## Project Timeline
PHASE |  |  | Aut | [14 empty] | Spr | [13 empty] | Sum
|  |  | Term Time | [9 empty] | Term Break |  |  |  |  | Term Time | [9 empty] | Term Break |  |  |  | Term Time
| PROJECT WEEK: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Study Stage | i | Term Time 7: PROJECT END
ii | bar: Term Time 4
iii | bar: Term Break 12
2 | Design Stage | i | bar: Term Time 1
ii | bar: Term Time 1
iii | bar: Term Time 2
iv | bar: Term Time 2
3 | Simulation Stage | i | bar: Term Time 5
ii | bar: Term Time 5
4 | Optimisation Stage | i | bar: Term Time 6
ii | bar: Term Time 6
5 | Comparison Stage | i | bar: Term Time 7
ii | bar: Term Time 7
iii | bar: Term Time 7
6 | Analysis Stage | i | bar: Term Time 8
ii | bar: Term Time 8
iii | bar: Term Time 8